## Launch Plan
LAUNCH PLAN
Task | Audience | Method(s) | Optional/Required | Recommended Sender | Recommended Timing | Date | Status
Pre-Launch Announcement(s) | Senior Leaders | Email/Meeting/Instant Messaging Channel | Strongly Recommended | Executive Sponsor | 2 - 4 weeks pre-launch |  | Not Started
| People Managers | Email/Meeting/Instant Messaging Channel | Strongly Recommended | Executive Sponsor | 2 - 4 weeks pre-launch |  | Not Started
| All Eligible Members | Email/Meeting/Instant Messaging Channel | Strongly Recommended | Executive Sponsor | 2 - 4 weeks pre-launch |  | Not Started
| All Eligible Members | Intranet/Newsletter | Optional | Program Manager | 2 - 4 weeks pre-launch |  | Not Started
Launch Announcement(s) | All Eligible Members | Meeting | Optional | Executive Sponsor + Program Manager | Launch Week |  | Not Started
| Senior Leaders | Email/Meeting/Instant Messaging Channel | Optional | Executive Sponsor + Program Manager | Launch Week |  | Not Started
| People Managers | Email/Meeting/Instant Messaging Channel | Optional | Executive Sponsor + Program Manager | Launch Week |  | Not Started
| All Eligible Members | Email/Meeting/Instant Messaging Channel | Strongly Recommended | Executive Sponsor + Program Manager | Launch Week |  | Not Started
| All Eligible Members | Intranet/Newsletter | Strongly Recommended | Executive Sponsor + Program Manager | Launch Week |  | Not Started
Invitations | All Eligible Members | 10KC | Required | 10KC | Launch Day |  | Not Started
| All Eligible Members | 10KC | Required | 10KC | 2 - 3 Days after Invites |  | Not Started
| All Eligible Members | 10KC | Required | 10KC | 5 - 7 Days after Invites |  | Not Started
Deadline to Claim Profile | All Eligible Members | n/a | Required | n/a | 10 - 14 Days after Invites |  | Not Started
Development Program Match Emails | Mentors + Mentees | 10KC | Required | 10KC | 3 - 7 Days after Deadline |  | Not Started
Careers Page | Applicants | Careers Page | Optional | Program Manager | Post-Launch |  | Not Started
New Hire Packages | New Hires | New Hire Packages | Strongly Recommended | Program Manager/HR | Post-Launch |  | Not Started
Social Media Post | Followers | LinkedIn/Facebook/Twitter/Instagram | Optional | Program Manager/Comms Lead | Post-Launch |  | Not Started